| Begin with the End in Mind: Backwards Design Timeline – EXAMPLE |  |  |  |
| --- | --- | --- | --- |
| Goal: |  |  |  |
| Identify the major elements that need to be completed: |  |  |  |
| Element | Time it will take to complete | Start Date | Date to be completed (Project End Date) |
| Bootcamp students complete post project | One month | Mid May | Mid June (6/16/2025) |
| Hands-on Training | Two Days | May 13th | May 14th |
| Students should complete online portion of curriculum | 6 to 8 weeks | April 7th | May 9th |
| Students emailed with important course information and asked to register for online platform | 1 to 2 weeks prior | Week of March 24th | April 7th |
| Registration Closes and Final Participant list created | 2 weeks prior | March 24th | March 24th |
| Bootcamp Marketing/Registration | Opens two months prior | February 1st | February 1st |
| Registration Form Created | one week prior to registration | Week of Jan | February 1st |
| Marketing materials created | One month prior to registration open | January 1st | February 1st |
| Curriculum developed/determined | About Two months before marketing starts | Nov 1st | December 31st |

| Begin with the End in Mind: Backwards Design Timeline |  |  |  |
| --- | --- | --- | --- |
| Goal: |  |  |  |
| Identify the major elements that need to be completed: |  |  |  |
| Element | Time it will take to complete | Start Date | Date to be completed (Project End Date) |